## Sheet1
Thurston/Mason System of Care Partnership (FYSPRT) Work Plan - January 2021 through December 2022
Goals | Action Steps | Those Assigned | Timeline for Completion
Increase representation of marginalized populations by Increasing use of culturally competent strategies for outreach to historically marginalized populations for participation in the SOCP. | 1. Send invitations and agendas to Native American Tribes within the region, i.e. Skokomish Indian Tribe, Squaxin Island Tribe and Nisqually Indian Tribe. Contact any Tribal representative to let them know they are missed if they are not present at a monthly SOCP meeting. 2. Support current participants who are people of color, participants who identify as LGBTQIA2S+, people who are houseless or organizations who support people who are houseless, with invitations and contact between meetings. 3. Support individuals with disabilities with any accommodations necessary to assure participation in monthly SOCP meetings. 4. Provide meeting setting accommodations and additional contact for marginalized populations who are in Tri-lead positions. 5. Continue recruitment of marginalized population representatives. | The convener has been in touch with a therapist from the Nisqually Tribe who has promised to have the Behavioral Health Director call but that did not happen prior to the April meeting. | April 2024 Update: A representative from the Squaxin Island Tribe participated in this meeting. The Skokomish Tribe participant was unable to make it to the March meeting but promised to be at the April meeting and was not present. System, family and youth BIPOC participants were present at the April meeting. .
Increase youth recruitment and participation in the System of Care Partnership. | 1. Send invitations and agendas to youth and young adults for monthly SOCP meetings. C 2. Encourage youth/young adults to participate as Tri-leads. 3. Consult with Youth Move National and share their youth engagement webinars. 4. Add text group to top of the meeting agenda with contact name and number for youth. | Montgomerie Rasmussen-Mason Youth, Donna Obermeyer-Convener and Heidi Knadel, Catholic Community Services Director. | April 2024 Update: There were two additional youth that attended this meeting in-person.. One of the Co-System Tri-leads who is also the Director for Catholic Community Services announced during the April meeting that CCS is planning to pull a group of youth who are current and former recipients of WISe together. Pizza will be provided and the purpose would be for the youth to share what could be helpful and what they want the system to know. The youth text group information is at top of the meeting agenda with contact name and number for youth. All youth continue to be invited and there is regular communication with the Youth Tri-lead. | ,
Over-arching goal: More mental health awareness and fluency taught in schools, to parents and to staff. The Ending the Silence presentation with NAMI Mason/Thurston is a good starting point. | 1. Identify school behavioral health programs by implementing a standing monthly SOCP agenda item for school resource sharing. 2. Encourage ESD 113 and school districts to share programs and updates. 3. Invite additional districts to the SOCP meetings. | The Convener will make sure the monthly agenda includes schools sharing resources and work on inviting more districts to the SOCP. Tri-leads will strongly encourage ESD 113 and school district representatives to share resources and program updates. | April 2024 Update:  The Shelton School District representative let the group know they hosted a Vaping 101 presentation and Washington Poison Control was there to share about how to talk with youth about drug use in an evidence based way. They gave families tools about the relationship between substance use and mental health. Poison Control can work with other school districts. Fentanyl and Marijuana will be discussed next school year in addition to Vaping 101. Usage is up and involves students down to the fifth grade level. She also mentioned that there are programs for youth ages 13 and up but not for youth ages 6 and 7. This is a severe gap. o Further comments were about the Mason County Substance Use Coalition discusses how youth and young adults are getting vapes and understanding the need to lock up vapes and edibles. o A parent told the group that her eight year old neighbor had Fentanyl in a vape as is in the intensive care unit at the hospital. o Another parent shared that their own child’s school friend’s parents provide them and they ARE laced and it is not just nicotine. She said she would love more intervention. The North Thurston Public School District and Yelm School District participants were present but did not share information at this meeting. The Olympia School District and ESD 113 participoants were not able to make it to the meeting.
Identify goal language that the SOCP can accomplish for the Area of Focus: More mental health providers available to young people and their families regardless of income and health insurance. This would be a change in the system as well as services rendered. | The group will be reminded of strategies and comments made during the March meeting and brainstorm more strategies focusing on the two items voted for (the hub and data) via email using Poll Everywhere to encourage comments that are anonymous typing into the poll and also using anonymous texting and discussion that will move the group forward. | Jacque Ward, Co-Family Tri-lead to check the hub website, making sure information is accurate or if it needs to be updated. Heidi Knadel, Co-System Tri-lead to assist providers n connecting with the hub website to post/update their information. | April 2024 Update: The group was polled during the meeting and chose to eliminate data for the present time and focus on the hub website as a way to make sure caregivers and providers could find resources. Here are the comments and strategies for the hub using Poll Everywhere. Hub Brainstorming • Spreading awareness of the Hub • Needs a point person • Determine next steps for updating provider info/services. Youth Navigator Program help? Monitor traffic to website? • Share the hub as far and wide as we can, and include as much data as we can all in one place. Maybe include data from matrix, telehealth research, and social media research. Maybe even share perspectives from youth and families, in like a blog area? For other youth and families looking at the hub • List services that provide telehealth on the hub • Create a comprehensive list of telehealth services and providers to share. • Providing a more user friendly interface. • More resources for family members who are caring for people in active substance abuse or negative mental health behaviors and how to keep balance for the family. • Making a large click button when someone goes to the page, like CLICK HERE TO SEARCH SERVICE OPTIONS • Let's check off what is on the hub already today if we can • Increase marketing for the HUB • A point person or group to periodically review and update